## Slide 1: Agenda
Administrative
  Syllabus
  Poll Everywhere
Introduction to Agile Project Management

## Slide 2: Poll Everywhere
Detailed instructions available via eLearning
  Must create a registered account
  Cost $14
Respond via laptop, tablet or smartphone browser
  www.pollev.com/thouin

## Slide 3: Project Success
Under what conditions is a project deemed to have been successful?

## Slide 4: Project Performance Varies Greatly
Notes: Part of a survey of 5,400 IT projects with budgets greater than $15 million
“On average, large IT projects run 45 percent over budget and 7 percent over time, while delivering 56 percent less value than predicted. Software projects run the highest risk of cost and schedule overruns1.” http://www.mckinsey.com/insights/business_technology/delivering_large-scale_it_projects_on_time_on_budget_and_on_value

## Slide 5: Causes of Cost Overruns

## Slide 6: Project Success Factors
Notes: How do we define project success?

## Slide 7: What is a Project?
Project Defined
  A complex, nonroutine, one-time effort limited by time, budget, resources, and performance specifications designed to meet customer needs.
Major Characteristics of a Project
  Has an established objective
  Has a defined life span with a beginning and an end
  Requires across-the-organizational participation
  Involves doing something never been done before
  Has specific time, cost, and performance requirements

## Slide 8: What is Project Management?
Project management is the application of knowledge, skills, tools and techniques to project activities to meet the project requirements
PMBOK Guide, 5th Edition

## Slide 9: The Role of Projects in Organizations
Organizational Mission, Vision, Core Values, Objectives
  Organizations create strategic plans to achieve objectives
  Portfolio, program and project management ensures alignment with strategic plan
Portfolio Management
  Collection of programs that are grouped together to facility effective management and alignment with strategic plan (e.g. Microsoft Business Solutions)
Program Management
    Collection of projects that are grouped together to facility effective management and alignment with strategic plan (e.g. Microsoft Office 2016)
Project Management
  Focus on achieving project objectives (e.g. Microsoft Word 2016)

## Slide 10: Project Success
At or under budget
At or ahead of schedule
All required features and benefits
Stakeholder satisfaction

## Slide 11: Software Project Management

## Slide 12: Software Project Management
Project Management
  PMI PMBOK
  5 Process Groups, 10 Knowledge Areas
Project Delivery
  Systems Development Lifecycles (SDLC)
    Waterfall
    Iterative
    Scrum

## Slide 13: Project Management

## Slide 14: Project Management - Process Groups
Initiating
Planning
Executing
Monitoring/Controlling
Closing
PMP in Depth: Project Management Professional Study Guide for PMP and CAPM Exams

## Slide 15: Project Management Process Groups
Stage (Process Group) | Main Goal | Main Output
Initiating | Authorize the Project | Project charter and stakeholder register
Planning | Plan and schedule the work to perform the project | Project management plan that contains subsidiary plans, such as scope management plan and schedule management plan
Executing | Perform the project work | Project deliverables: product, service, result
Monitoring and Controlling | Monitor the progress of the project to identify the variance from the plan and to correct it | Change requests and recommendations for preventive and corrective action
Closing | Close the project formally | Product acceptance and contract closure
PMP in Depth: Project Management Professional Study Guide for PMP and CAPM Exams

## Slide 16: Big Picture of Project Management
PMP in Depth: Project Management Professional Study Guide for PMP and CAPM Exams
Stakeholder Management
Notes: 5 Process Groups, 10 Knowledge Areas, 47 Processes

## Slide 17: The Triple Constraint (The Iron Triangle)
Quality Software Project Management

## Slide 18: Project Delivery

## Slide 19: Project Delivery - Waterfall SDLC
Requirements
Design
Develop
Test
Implement

## Slide 20: Project Delivery – Scrum SDLC
Source: Essential Scrum by Kenneth S. Rubin p. 17
Notes: Agile software development emphasizes agility and the ability to adapt to changing conditions
  Time boxed deliverables
  Limited up-front planning, frequent product deliverables, limited documentation, and quick daily meetings with team and customers

## Slide 21: Project Roles

## Slide 22: The Project Manager
Person responsible for achieving project objectives
  Different from a functional manager
  Different from a Scrum Master
  Must be able to effectively use and apply project management principles
Interpersonal skills
  Leadership Political and cultural awareness
  Team building Negotiation
  Motivation Trust building
  Communication Conflict Management
  Influencing Coaching
  Decision making
PMP in Depth: Project Management Professional Study Guide for PMP and CAPM Exams

## Slide 23: Scrum
Scrum Master
  Helps everyone involved understand Scrum values, principles and practices
  Coach, servant leader, process authority, impediment remover, influencer
Product Owner
  Single point of product leadership
Developers
  Perform the work required to build the software product

## Slide 24: Exercise
Quantum Bank

## Slide 25: Group Project Signup
Group Projects
Microsoft Project Professional 2019
Poll Everywhere